## Assignment 1 - Bugs Report
Bugs Report
Bugs ID | Bugs Title | Bugs Description | Bugs Preconditions | Steps to Reproduce | Expected Result | Actual Result: | Bug Severity | Bug Priority | Attachments | Status | Assigned To:
B-001 | Login not available using a username. | In login page , user can't login to their account using username . | Create account and open login page . | 1.Open the login page . 2.Enter a valid username and password . 3.Click sign in with email button . | The user should be successfully logged into their account | The user is unable to access their account using username. | High | High | bug_001 | Open | Evekey
B-002 | Reset password not allow users to successfully reset their password . | Confirmation link not be sent to the user's email when the user want reset email . | Create account and open login page . | 1.Creat account and open login page . 2.Click the reset password . 3.Enter a valid email . 4.Click get password link . | A confirmation link should be sent to the user's email . | A confirmation link not be sent to the user's email. | High | High | I will cheak the api response and payload if avalible | Open | Evekey
B-003 | Reset password should not allow using the username as a valid input. | This ensures that the process is correctly handled using the email address only. | Create account and open login page . | 1.Creat account and open login page . 2.Click the reset password . 3.Enter a username . 4.Click get password link . | Hint should be "enter the email" not username . | Hint "enter the email or username" and message " error not found" . | Medium | Medium | bug_003 | Open | Evekey
B-004 | The sort by 'high to low 'and 'low to high' filter is not working when a product is specified from the search bar. | "When searching for a product and selecting the filter 'Sort by High to Low' or 'Low to High', the filter is not working. | Search the product then apply sort by 'high to low 'and 'low to high' filter . | 1. Search the product from search bar . 2. Click on filter . 3. Apply sort by 'high to low 'and 'low to high' . | In the 'High to Low' sort, the prices appear in descending order, and in the 'Low to High' sort, the prices appear in ascending order. | Both of sort type the price appear without sort. | High | High | bug_004 | Open | Evekey